## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
US ID | SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  |  | AS A/AN | I WANT TO | SO THAT
1 | 1 | SB1/US1 | Passanger | Can Register Themselve With Email Id | I Can Receive A Confirmation/Verification Mail
2 | 1 | SB1/US2 | Passanger | Receive A Confirmation Mail | I Can Access The Live BUS STATUS APP
3 | 1 | SB1/US3 | Passanger | Login Into The System Using Mail Id And Password | I Can View/Edit My Profile
4 | 1 | SB1/US4 | Passanger | Modify The Account Password | I Can Keep My Account Secure
5 | 1 | SB1/US5 | Passanger | Check Location | I can check my location
6 | 1 | SB1/US6 | Passanger | Search Location | I can check other locations
7 | 1 | SB1/US7 | Passanger | View Routes | I can view the diffenernt different routes available on app
8 | 1 | SB1/US8 | Passanger | Select Route | I can view a particlar route and stops
9 | 1 | SB1/US9 | Passanger | View Buses | I can look for a bus
10 | 1 | SB1/US10 | Passanger | Select Bus | I can view a particlar route of a bus
11 | 1 | SB1/US11 | Passanger | View The bus timing | I Can Work According To The bus timing
12 | 1 | SB1/US12 | Passanger | View Bus On Road | I Can see the bus status
13 | 1 | SB1/US13 | Passanger | View The bus on time | Can see the delay time of the bus
14 | 1 | SB1/US14 | Passanger | Set Location on routes | I can see the available buses from that stop
15 | 1 | SB1/US15 | Passanger | Select Stop | I can view Bus Details and its fare
16 | 1 | SB1/US16 | Passanger | Search for routes | I can find buses on that route
17 | 1 | SB1/US17 | Passanger | Give Feedback/Suggestions | The Way Of Working Of The App
18 | 1 | SB1/US18 | Passanger | Discuss Among Other Passengers | I Can chat with friends who are on app
19 | 1 | SB1/US19 | DBA | Fire Insert Queries | I Can Insert New Records In The Database
20 | 1 | SB1/US20 | DBA | Fire Select Queries | I Can View The Records
21 | 1 | SB1/US21 | DBA | Fire Update Queries | I Can Keep The Database Updated
22 | 1 | SB1/US22 | DBA | Fire Delete Queries | I Can Remove Unwanted Data
23 | 1 | SB1/US23 | DBA | Take Backup | I Can Save The Old Records In The Database For Future Use
24 | 1 | SB1/US24 | DBA | Delete Backup | I Can Delete The Records Which Is Not Needed Any More
25 | 1 | SB1/US25 | DBA | Adding new routes | I Can Access The Digital College System
26 | 1 | SB1/US26 | DBA | Deleting routes which are no longer are taken | I Can Keep My Account Secure
27 | 1 | SB1/US27 | DBA | Adding new buses | Course Allotment Can Be Done
28 | 1 | SB1/US28 | DBA | Delete buses which are no longer in use | Load Allotment Can Be Done
29 | 1 | SB1/US29 | DBA | Managing Authentication of drivers | Time-Table Can Be Made
30 | 1 | SB1/US30 | DBA | Addind Drivers with their details and respective driver IDs | I Can Monitor The Current Schedule
31 | 1 | SB1/US31 | DBA | Updating bus routes | Adding of new routes
32 | 1 | SB1/US32 | DBA | Updating bus status wheather it is functioning or not | Details of bus whether its on route or stop because of any fault
33 | 1 | SB1/US33 | DBA | Adding start time of respective buses and their stop time | updating info. Of bus
34 | 1 | SB1/US34 | DBA | Estimated journey time to reach the desired destination | timing of reaching a particular stop
35 | 1 | SB1/US35 | DBA | Adding the time for first bus to start and the last bus to start | timing of different buses
36 | 1 | SB1/US36 | Driver | can login in the app througn mail id | I can view/Edit My Profile
37 | 1 | SB1/US37 | Driver | can add his bus details | he can see the bus he is travelling
38 | 1 | SB1/US38 | Driver | can add routes | I can see on which routes I am travelling
39 | 1 | SB1/US39 | Driver | can add my bus details | I can my details of travelling
40 | 1 | SB1/US40 | Driver | I can see my route | visualise my live tracking
41 | 1 | SB1/US41 | Driver | update bus details after completion of my time | I can update the next driver information
42 | 1 | SB1/US42 | Driver | working hours | I can see how my hours I have worked
43 | 1 | SB1/US43 | Driver | Daily routine | I can see what I have done all day
44 | 1 | SB1/US44 | Driver | Give Feedback/Suggestions | The Way Of Working Of The App
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Digital College>
SB1/US1 |  | SB1/D1/T1
SB1/D1/T2
SB1/D1/T3
SB1/D1/T4
SB1/US2 |  | SB1/D2/T1
SB1/D2/T2
SB1/D2/T3
SB1/D2/T4
SB1/US3 |  | SB1/D3/T1
SB1/D3/T2
SB1/D3/T3
SB1/D3/T4
SB1/US6 |  | SB1/D4/T1
SB1/D4/T2
SB1/D4/T3
SB1/D4/T4
SB1/US7 |  | SB1/D5/T1
SB1/D5/T2
SB1/D5/T3
SB1/D5/T4
SB1/US27 |  | SB1/D6/T1
SB1/D6/T2
SB1/D6/T3
SB1/D6/T4
SB1/US27 |  | SB1/D7/T1
SB1/D7/T2
SB1/D7/T3
SB1/D7/T4
SB1/US150 |  | SB1/D8/T1
SB1/D8/T2
SB1/D8/T3
SB1/D8/T4
SB1/US28 |  | SB1/D9/T1
SB1/D9/T2
SB1/D9/T3
SB1/D9/T4
SB1/US50 |  | SB1/D10/T1
SB1/D10/T2
SB1/D10/T3
SB1/D10/T4
SB1/US53 |  | SB1/D11/T1
SB1/D11/T2
SB1/D11/T3
SB1/D11/T4
SB1/US55 |  | SB1/D12/T1
SB1/D12/T2
SB1/D12/T3
SB1/D12/T4
SB1/US51 |  | SB1/D13/T1
SB1/D13/T2
SB1/D13/T3
SB1/D13/T4
SB1/US70 |  | SB1/D14/T1
SB1/D14/T2
SB1/D14/T3
SB1/D14/T4
SB1/US71 |  | SB1/D15/T1
SB1/D15/T2
SB1/D15/T3
SB1/D15/T4
SB1/US72 |  | SB1/D16/T1
SB1/D16/T2
SB1/D16/T3
SB1/D16/T4

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup
Search about components required
Purchase component from Market
Develop the hardware
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application
search paint application
search video making application
search audio recording applications
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials
Study tutorials
start with Basics of c#
start with Basics of c#
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of c#
start with Basics of c#
|  | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
Debug the code
Debug the code
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen
Interface it with PC/laptop
Switch on the projector and set the projected screen
Interface it with PC/laptop
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen
Use different applications on the virtual screen
Check the changes made at the virtual screen
Checking if it is working effectively with the laptop and not damaged
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables
Prepare all software deliverables
Prepare a hardware & software guide
Prepare a user manual & guide for the users
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project
Project demonstration
Project demonstration
Project to be operated by different users
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 180 | 180 | Tasks
2018-09-12 | 120 | 180
2018-09-11 | 80 | 180
2018-09-14 | 56 | 180
2018-09-16 | 15 | 180
2018-09-18 | 5 | 180
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <Digital College>
| Add Department | SB2/D1/T1 | Designing the GUI | SP
|  | SB2/D1/T2 | Connection with database to fetch the data | RA
|  | SB2/D1/T3 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Register TA into the application(using poornima email account) | SB2/D2/T1 | Designing of GUI | PB
|  | SB2/D2/T2 | Validating user input at client level | RM
|  | SB2/D2/T3 | Validating user input at server level | SP
|  | SB2/D2/T4 | Connection with Database to insert the record. | RA
|  | SB2/D2/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| TA Receiving Confirmation Email | SB2/D3/T1 | Designing of Email(to be send) | PB
|  | SB2/D3/T2 | Send Email via coding using the Mandrill App | SP
|  | SB2/D3/T3 | Connection with database to update the status in the database. | RA
|  | SB2/D3/T4 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Register TO into the application(using poornima email account) | SB2/D4/T1 | Designing of GUI | PB
|  | SB2/D4/T2 | Validating user input at client level | RM
|  | SB2/D4/T3 | Validating user input at server level | SP
|  | SB2/D4/T4 | Connection with Database to insert the record. | RA
|  | SB2/D4/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| TO Receiving Confirmation Email | SB2/D5/T1 | Designing of Email(to be send) | PB
|  | SB2/D5/T2 | Send Email via coding using the Mandrill App | SP
|  | SB2/D5/T3 | Connection with database to update the status in the database. | RA
|  | SB2/D5/T4 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Add Subject | SB2/D6/T1 | Designing of GUI | PB
|  | SB2/D6/T2 | Validating user input at client level | RM
|  | SB2/D6/T3 | Validating user input at server level | SP
|  | SB2/D6/T4 | Connection with Database to insert the record. | RA
|  | SB2/D6/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Register Timetable Co-ordinator into the application | SB2/D7/T1 | Designing of GUI | PB
|  | SB2/D7/T2 | Validating user input at client level | RM
|  | SB2/D7/T3 | Validating user input at server level | SP
|  | SB2/D7/T4 | Connection with Database to insert the record. | RA
|  | SB2/D7/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Timetable Co-ordinator Receiving Confirmation Email | SB2/D8/T1 | Designing of Email(to be send) | PB
|  | SB2/D8/T2 | Send Email via coding using the Mandrill App | SP
|  | SB2/D8/T3 | Connection with database to update the status in the database. | RA
|  | SB2/D8/T4 | Testing of the module on localhost and then on server. | RA+SP+PB+RM

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 177 | 177 | Tasks
2017-09-28 | 110 | 177
2017-10-02 | 80 | 177
2017-10-05 | 66 | 177
2017-10-07 | 15 | 177
2017-10-09 | 5 | 177
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Digital College>

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 120 | 120 | Tasks
2018-10-18 | 110 | 120
2018-10-20 | 80 | 120
2018-10-21 | 25 | 120
2018-10-22 | 15 | 120
2018-10-23 | 0 | 120
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Digital College>

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 190 | 190 | Tasks
2019-01-11 | 110 | 190
2019-01-12 | 80 | 190
2019-01-13 | 25 | 190
2019-01-14 | 15 | 190
2019-01-15 | 0 | 190
0
Days